WASHINGTON TURGRASS SEED COMMISSION

PROGRESS REPORT

Project No.: 3267

Title: Weed Management in Turfgrass for Seed

Personnel: Ian Burke, Professor

Reporting Period: August 1, 2021 to July 30, 2022

Accomplishments:

- Evaluated Zidua crop safety in Kentucky bluegrass in collaboration with FMC.

- Evaluated Kentucky bluegrass response to timing of Moddus application.

- Initiated the second trial required for a Special Local Needs label for Outrider use in Kentucky bluegrass in Washington.

- Installed additional trials to continue to evaluate Talinor and Alion.

- Installed sufficient trials to hold a Weed Science Field Day in Spokane County.

Results:

In 2022, multiple field trials were conducted to study Zidua (pyroxasulfone), Outrider (sulfosulfuron), Alion (indaziflam), Moddus, and Talinor for grass and broadleaf weed management and crop safety in turfgrass for seed. Our results indicate:

1) Axial Bold could be used in Kentucky bluegrass, but timing of application may be limited to late summer, fall, or very early spring due to crop safety. A ½ labeled rate was also safer than a 1x rate. Summer or fall applications for control of emerged winter annual grass weeds may be possible. Axial Bold remains a high risk product for continued research.

2) No newly seeded Kentucky bluegrass response was observed when treated with Outrider, an important discovery for the control of winter annual grass weeds, particularly ventenata. The use of Outrider would occur as part of a herbicide system to manage ventenata. A Special Local Needs label is approved in Oregon, and we will submit for Washington upon completion of the 2023 harvest.

3) Talinor is a very effective broadleaf herbicide, and is particularly effective on mayweed chamomile, a noxious weed in Nevada and Colorado. We will continue to evaluate spring applications of Talinor for broadleaf weed control and crop safety.

4) Alion is an effective seedling selective herbicide. A trial was initiated in established Kentucky bluegrass to understand long term stand response and weed control in dryland Kentucky bluegrass.

5) Moddus was evaluated in two different timings of application. Earlier applications resulted in reduced stand height, with greater variability in stand height reduction observed with a later application timing.

Publications:

For detailed reports of our work for the Turfgrass for Seed Commission, please visit the Small Grains website: Lyon et al. 2022. Annual Weed Control Report. http://smallgrains.wsu.edu/weed-resources/weed-publications/weed-control-reports/

Washington Turfgrass Seed Commission

Progress Report Format for 2022 Projects

| Name: Ian C. Burke |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SUPPORTING AGENCY AND AGENCY ACTIVE AWARD/PENDING PROPOSAL NUMBER |  | TOTAL $ AMOUNT | EFFECTIVE AND EXPIRATION DATES | % OF TIME COMMITTED | TITLE OF PROJECT |
| Active: Washington Grain Commission USDA-OREI Washington Grain Commission USADPL USDA-AFRI Washington Turfgrass Seed Commission USDA-OREI |  | $ 64,775 1,555,000 39,832 24,000 3.99M 16,691 2.0M | 7/22 – 7/23 10/19 – 10/24 7/22 - 7/23 7/22 - 7/23 8/17 - 7/22 8/22-7/23 8/18 - 7/23 | 6 6 6 3 6 3 7 | Weed Control in Wheat Compost carryover and cover crop effects on soil quality, profitability, and cultivar selection Herbicide Resistance and Susceptibility in Wheat and Weeds Weed Management in Pulses Inland Pacific Northwest Wheat-Based Systems: Landscapes In Transition Weed Management in Turfgrass for Seed CREEP STOP: Evaluating new methods to manage perennial weeds |
| Submitted: Washington Turfgrass Seed Commission Washington Oilseed Commission |  | $ 19,026 $24,000 | 8/23-7/24 8/23-7/24 | 3 3 | Weed Management in Turfgrass for Seed Canola Variety Testing |